Good Practice / Guidance Completing the Report

The target is for consistency in how we capture the reporting narrative.

- The SRO / SPA (use as appropriate) DCA remains as / has changed / improved / deteriorated ……… because ………

- The first project benefit (i.e., first package, operational readiness, transition) milestone is … (protected / at risk).

- P50 completion cost has (… increased by xxx / been maintained in period) as a result of (… e.g., ongoing construction productivity issues and P50 schedule prolongation). Action is being taken ……

- P50 schedule position has improved / deteriorated in period due to …… The implications of this to contingency, risk and resources are …… Action being taken …… with the following opportunities being pursued ……

- The Baseline RAG status against SL P50 Project Baseline is ……… due to ………………, additionally (if applicable) this will change when ………

- Highlights / issues in period …… Capability & Capacity RAG status is ……… due to ……………

When completing the report please ensure:

- The narrative is appropriate to the audience; they will not necessarily know the detail you do.

- Alignment is maintained between messaging and RAGs (where the project is reported as part of the Government Major Projects Portfolio Reports (GMPP)).

- The comments are at an “official” level of security.

- All acronyms are expanded on first use in the individual project commentaries (consider the audience).

- Do not include building numbers.

- Do not include document reference numbers.

- Any figures included in the narrative match the figures brought through from the app.

- All dates are to be described in full, e.g., 15th May 2024.

- The performance summary should read as a flowing paragraph, not in bullets.